## Project_Work_Order6386123531157
Project Work Order
From 07 Aug 2024 To 07 Sep 2024
Page 1 of 1
Total Records: 5 Records 1 To 5
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
Adiyogi | 19 | 0 | 01 May 2024 | Kumel Alam | Ninth Floor Labour RCC Work For Department Work | Labour RCC Work For Department Work | NOs | 16 | 800 | 12800 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  |  |  | Amol.Mandlik | Amol.Mandlik | construction open | 25 Jun 2024 |  | RCC | Approved | Amol.Mandlik |  | 100
Adiyogi | 27 | 0 | 01 Jun 2024 | Kumel Alam | Tenth Floor Labour RCC Work For Department Work | Labour RCC Work For Department Work | NOs | 27 | 800 | 21600 | 0 | 21600 | 0 | 27 | 21600 | 0 | 0 | 0 | 21600 | 0 | 0 |  |  |  | Amol.Mandlik | Amol.Mandlik | construction open | 20 Jul 2024 |  | RCC | Approved | Amol.Mandlik |  | 100
Adiyogi | 27 | 0 | 01 Jun 2024 | Kumel Alam | Tenth Floor RCC Labour Fitter Area Wise | RCC Labour Fitter Area Wise | SQF | 3787 | 39 | 147693 | 0 | 147693 | 5 | 3787 | 147693 | 0 | 0 | 0 | 147693 | 0 | 0 |  |  |  | Amol.Mandlik | Amol.Mandlik | construction open | 20 Jul 2024 |  |  | Approved | Amol.Mandlik |  | 100
Adiyogi | 36 | 0 | 01 Jul 2024 | Kumel Alam | Eleventh Floor Labour RCC Work For Department Work | Labour RCC Work For Department Work | NOs | 13 | 800 | 10400 | 0 | 10400 | 0 | 13 | 10400 | 0 | 0 | 0 | 10400 | 0 | 0 |  |  |  | Amol.Mandlik | Amol.Mandlik | construction open | 20 Aug 2024 |  | RCC | Approved | Amol.Mandlik |  | 100
Adiyogi | 36 | 0 | 01 Jul 2024 | Kumel Alam | Eleventh Floor RCC Labour Fitter Area Wise | RCC Labour Fitter Area Wise | SQF | 3212 | 39 | 125268 | 0 | 125268 | 5 | 3212 | 125268 | 0 | 0 | 0 | 125268 | 0 | 0 |  |  |  | Amol.Mandlik | Amol.Mandlik | construction open | 20 Aug 2024 |  |  | Approved | Amol.Mandlik |  | 100