## RABillBrowse_Contwise6386123525
Contractor RA Bill
Adiyogi
Page 1 of 1
Total Records: 4 Records 1 To 4
Contractor | WO NO | RA Bill | RA Bill Date | Voucher_No | Project | Labour_Name | TASK | Revision | Qty | Unit | Rate | Payment Schedule | PS % | Retaintion | Retention_amt | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Net Amount | Status | Credits | Debits | TDS_Amt
Kumel Alam | 27 | 459 | 2024-08-08 |  | Adiyogi | Labour RCC Work For Department Work | Tenth Floor Labour RCC Work For Department Work | 0 | 27 | NOs | 800 | RCC Bill Book | 100 | 0 | 7384.65 | 21600 | URD | 0 | 21600 | 21600 | Unapproved | 0 | 0 | 0
Kumel Alam | 27 | 459 | 2024-08-08 |  | Adiyogi | RCC Labour Fitter Area Wise | Tenth Floor RCC Labour Fitter Area Wise | 0 | 3787 | SQF | 39 | RCC Bill Book | 100 | 7384.65 | 7384.65 | 147693 | URD | 0 | 147693 | 140308.35 | Unapproved | 0 | 0 | 0
Kumel Alam | 36 | 460 | 2024-08-08 |  | Adiyogi | Labour RCC Work For Department Work | Eleventh Floor Labour RCC Work For Department Work | 0 | 13 | NOs | 800 | RCC Bill Book | 100 | 0 | 6263.4 | 10400 | URD | 0 | 10400 | 10400 | Unapproved | 0 | 0 | 0
Kumel Alam | 36 | 460 | 2024-08-08 |  | Adiyogi | RCC Labour Fitter Area Wise | Eleventh Floor RCC Labour Fitter Area Wise | 0 | 3212 | SQF | 39 | RCC Bill Book | 100 | 6263.4 | 6263.4 | 125268 | URD | 0 | 125268 | 119004.6 | Unapproved | 0 | 0 | 0